## Slide 1: JOINME2 TPM5
Bremen, Germany
16-17 March, 2023

## Slide 2: Agenda 16 March, 2023 Thursday
9:30 -10:00 Welcoming and Introduction
10:00-11:30 Updates on the training modules
Labor distribution (training evaluation)
11:30-11:45 Coffee Break
11:45-13:15 Budgetary Issues
13:15-14:30 Lunch Break
14:30-17:00 Conference Preparations
19:30 Dinner

## Slide 3: Updates on the training modules
Feedback
No major revisions needed on content

## Slide 4: Plan for piloting
Finding the volunteers
10 per country
Passwords
Keep track of the code holders
Dates
Reporting the Results
Evaluation
March, 20-April, 30
Module
Training
1
2
3
4
5

## Slide 5: The process
Every partner institution will receive 10 passwords
Passwords to be distributed to 10 different faculty members
Deadline April,30 2023
We will receive the pre-post test results
Evaluation of the data
Presenting at JOINME2 Conference

## Slide 6: Labor distribution (training evaluation)
Each group working on modules will be responsible for the evaluation of their own module survey.
Onboarding (Ali, Marta, Nesrin) + Offboarding (Geri, Aynur): pre-post test
Disability: Gökçe – Rojda
Sexual Orientation: Oliver-Kristof
Sex, Gender, Identity: Franzi – Anna
Race, Ethinicity and Culture: Maria-Vana

## Slide 7: Timeline
End of Project
March, 20
Starting the piloting
April, 30
End of Piloting
May,30
Evaluation
June, 14-16
Conference, TPM in İzmir
August, 30

## Slide 8: COFFEE BREAK

## Slide 9: Budgetary Issues 1 Travels (Including Bremen)
Getting ready for the final Report
Belgium: 8 travels - 4 used
Antalya: 8 travels - 6 used
Poland: 8 travels – 4 used
Greece: 8 travels - 3 used
Germany: 10 travels - 4 used
UK: 10 travels - 3 used

## Slide 10: Budgetary Issues 2 Staff Cost
Getting ready for the final Report
Belgium: 85
Antalya: 55 Researcher+ 40 Technician
Poland: 85
Greece: 85
Germany: 85-5
UK: 85-5

## Slide 11: LUNCH BREAK

## Slide 12: CONFERENCE
How to promote?
Conference website
Program
Keynotes
Conference Dinner

## Slide 13: How to Promote
Contacting universities
Social Media
Personal Contacts

## Slide 14: Cıonference Web Page
https://joinme2.org/

## Slide 18: CONFERENCE PROGRAM

## Slide 19: KEYNOTE 1 15 June, 2023 Associate Professor BURAK KARABEY BUCA FACULTY OF EDUCATION DEPARTMENT OF SPECIAL EDUCATION Dr. Burak Karabey is a researcher at Dokuz Eylül University , Faculty of Education. He did his PhD degree on Creative and Critical Thinking Style of Gifted Children in Primary and Secondary School. He is also interested in “Problem Based Learning, Problem Solving, Critical Thinking, Mathematics Education and Teacher Education” He has been involved various international and national projects related to Creativity, Innovation, Social Inclusion and teacher training.

## Slide 20: KEYNOTE 2 ???

## Slide 21: Food for Thought
Conference Dinner?

## Slide 22: Thank you