## Slide 1: 6th TPM 14 June, 2023, IZMIR
JOINME2

## Slide 2: WEDNESDAY, june, 14
9:30 – 10:00
Welcoming
10:00 – 11:00
Analysis of Qualitative and Quantitative data on modules
10:00-10:20 On/Offboarding
10:20-10:30 Disability
10:30-10:40 Sexual Orientation
10:40-10:50 Biological sex, gender
10:50-11:00 Race, Ethnicity & Culture
11:00 – 11:30
Coffee Break
11:30 – 13:00
Final Documentations of the Project
13:00 – 14:30
Lunch Break
14:30 – 18:00
Conference Preparations
Dissemination of the Project
Final venue check

## Slide 4: What DID we do so far?
Online Meetings
The Kick-Off Meeting
Catch-up Meeting
2nd TPM- Leuven
3rd TPM- Antalya
4th TPM- Mytilene
5th TPM- Bremen
6th TPM- İzmir
Output-1: The book
Output-2: Training Portal
Output-3:Trainings
Output-4: Knowledge Portal

## Slide 5: Budgetary ıssues
NA requires from partners to send us their budget info.
To be sure that the partners have already finished their first/second 40%

## Slide 6: Budgetary Issues
Payments made so far:
80% of total budget of each instituition
 | PMI | TPM | Intellectual Output | MultiplierEvent | Excp. Costs | TOTAL
IZMIR UNIVERSITY OF ECONOMICS | 17000 | 4970 | 16280 | 17500 | 0 | 56750
KATHOLIEKE UNIVERSITEIT LEUVEN | 8000 | 5710 | 18190 | 0 | 0 | 32900
PANEPISTIMIO AIGAIOU | 8000 | 5340 | 11645 | 0 | 0 | 25985
AKADEMIA POMORSKA W SLUPSKU | 8000 | 5340 | 6290 | 0 | 0 | 20630
UNIVERSITY OF BREMEN | 8000 | 6120 | 17120* | 0 | 0 | 32240*
UNIVERSITY OF DERBY | 8000 | 6860 | 17120* | 0 | 0 | 32980*
LİMON AĞACI DERNEĞİ | 8000 | 5340 | 6270 | 0 | 0 | 20610

## Slide 7: TIMESHEETS
 | OUTPUT 1 | OUTPUT 2 | OUTPUT 3 | OUTPUT 4 | TOTAL
PARTNERS | 01/09/2020- 31/05/2021 | 01/06/2021 30/06/2022 | 01.07.2022 01.01.2023 | 01/02/2023 31/08/2023 | 
IZMIR UNIVERSITY IF ECONOMICS | 65 | 65 | 0 | 90 | 220
KATHOLIEKE UNIVERSITEIT LEUVEN | 20 | 40 | 0 | 25 | 85
PANEPISTIMIO AIGAIOU | 20 | 40 | 0 | 25 | 85
AKADEMIA POMORSKA W SLUPSKU | 20 | 40 | 0 | 25 | 85
UNIVERSITY OF BREMEN | 15 | 40 | 0 | 25 | 80
UNIVERSITY OF DERBY | 15 | 40 | 0 | 25 | 80
LİMON AĞACI DERNEĞİ | 30 | 40 (Technician) | 0 | 25 | 95

## Slide 8: DOCUMENTATION
 | Greece | Belgium | Antalya | Poland | UK | Germany
Partnership Agreement | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
Affliation Form (Confirmation) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓3
Partner Change Acceptance Form | ✓ | ✓ | ✓ | ✓ | ✓ | not necessary
Mandate | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
Timesheets | x | x | x | x | x | x

## Slide 9: Closure OF THE PROJECT
AUGUST, 2023
Final Report to be submitted till September
Last 20% to be sent around new year based on the remaining sum

## Slide 10: WHAT TO DO TILL THE CLOSURE?
List of Expenses
Timesheets (Signed and Stamped) until August, 15th
Finalizing the papers for publication

## Slide 11: REMINDER
TO KEEP ALL THE DOCUMENTS FOR 3 YEARS

## Slide 13: CONFERENCE PREPARATIONS
Dissemination of the Project
Our Presentation
Conference venue Check

## Slide 14: What Can be done for the Dissemination of the Project?
Internal Evaluation Form

## Slide 15: Questıons for the fınal report
IMPACT
What was the project's impact on the participants, participating organisations, target groups and other relevant stakeholders?
What was the impact of the project at the local, regional, European and/or international levels? Please provide qualitative and quantitative indicators.
How did the project contribute to the achievement of the most relevant priorities as indicated in the description section?

## Slide 16: OUR PRESENTATION

## Slide 17: CLOSING REMARKS
ANY COMMENTS?

## Slide 18: JOINME2